## Master Plan
|  | Projects / Deliverables | Notes |  | Type (dropdown) | Covering Business Case |  |  |  |  | Individual Business Case |  |  |  | Master Schedule Fields & additional Master Data field re status | [15 empty] | Dates tbc | Dates Scheduled |  |  |  |  | Annual Performance Plan (APP) tracking |  |  | Primary, Secondary and Enduring outcomes | [7 empty] | Y1 (2025/26) Cost Breakdown (Forecast detail) | [7 empty] | YEAR 1 2025/26 1 Apr 2025 - 31 Mar 2026 | [6 empty] | YEAR 2 - 2026/27 | [9 empty] | Y4 (2028/29) Total Cost Estimates |  |  |  | Y5 (2029/30) Total Cost Estimates | Resource cost included (Y1) | Resource cost included (Y2) |  | Proposed Strategic Partner(s) | Procurement Vehicle? (Y/N) | TECHNICAL - ESTIMATES YEAR 1 2025/26 | [5 empty] | TECHNICAL ESTIMATES - YEAR 2 - 2026/27
Programme | Category | Projects / Deliverables | Description | Workshop Notes | Modernisation / Master Schedule | Name of Business Case | Approved Business Case (Y/N) | Date Approved / Anticipated Approval | BC Amount | Conceptual Design | Name of Business Case | Approved Business Case (Y/N) | Date Approved / Anticipated Approval | BC Amount | Conceptual Design (Exists? Y/N) | Project Started? (Y/N) | Approved BRS? (Y/N) | Progress to Date (i.e. current phase) | Project Manager | Portfolio Manager | Business Owner | Sponsor | Incident (existing/ new) | SQM&T confirmation | BC & Funding memo status - Marike | Systems Integrator | Cost Centre | Notes 1 | Category | Release Status | Previous scheduled date (col AH) | Dates Master Schedule / MVP dates ( New release dates ) | Prioritised | Y1/Y2 | Q1-Q4 | Core outcomes | APP-Planned | APP-Actual | APP-notes | Reduce the tax gap | Disrupt the illicit economy | Address rising tax debt | Broaden the tax base (bring unregistered into the system) | Reduce outstanding returns (non-filing) | Prevent impermissible refunds / refund fraud | Improve border effectiveness & facilitate legitimate trade | Increase enforcement resolution (recovery/prosecution success) | Spending YTD Actuals Roll-over | Spending YTD Actuals - New Approvals | Resource Augmentation Estimates | Vendor Cost Estimates | Hardware/ Software Cost Estimates | Roll-over Funding Actuals | New Funding Estimates | CHECK TOTALS | Q1 | Q2 | Q3 | Q4 | Augment Resources | Hardware | Y2 (2026/27) Total Cost Estimates | Q1 | Q2 | Q3 | Q4 | Augment Resources | Hardware | Y3 (2027/28) Total Cost Estimates | Vendor costs | Augment Resources | Hardware |  | Vendor costs | Augment Resources | Hardware |  |  |  | Previous (submitted) amount |  |  | Vendor A | Vendor B | Vendor C | Vendor D | Hardware | Y1 (2025/26) Total Cost Estimates (Rollover + New Funding excl. MS Costing) | Vendor A | Vendor B | Vendor C | Other | Hardware | Y2 (2026/27) Total Cost Estimates | Q1 2025/26 | Q2 2025/26 | Q3 2025/26 | Q4 2025/26 | ROI/ NPV | Total Project Duration & complexity | Mod / Leg / Op-Eff / Value Creation / Other | BC Weight | Filter