| Service Level Descriptions with Clause references to the Services Agreement and paragraph references to the RFP document. | Service Level Failures (Metrics) | Service Credits (expressed as a percentage of the Amount at Risk for a module) |
| --- | --- | --- |
| - Planning |  |  |
| - The Service Provider must supply and deliver a project management plan, including an implementation plan of the training programme with clear timelines of milestones, deliverables and activities. (Paragraph 9.3.2.3 of the RFP document) | The Service Provider supplies a project management plan but does not consult with SARS. | 20% |
|  | The Service Provider supplies a project management plan and consults with SARS but it does not contain clear timelines of milestones, deliverables and activities. | 40% |
|  | The Service Provider fails to supply a project management plan at all. | 60% |
| - The Service Provider must provide an orientation launch for each academic year. (Paragraph 9.2.2.2 of the RFP document) | The Service Provider provides an orientation launch but it does not include all SARS’s requirements, in SARS’s opinion. | 20% |
|  | The Service Provider fails to provide an orientation launch at all. | 60% |
| - Presentation of modules |  |  |
| - The Service Provider must supply and deliver learning material to all SARS Delegates at the commencement of the relevant module (Paragraph 9.2.2.3 of the RFP document). | The Service Provider fails to supply more than three (3) SARS Delegates with the learning material at the commencement of a module. | 20% |
|  | The Service Provider fails to supply the above mentioned SARS Delegates the learning material by close of business on the first day of the particular module. | 40% |
|  | The Service Provider fails to supply learning material to any of the SARS Delegates at the beginning of a module. | 60% |
| - The Service Provider must render the Services in line with agreed timeframes (Clause 4.4 of the Services Agreement). | The Service Provider does not adhere to timeframes in respect of two (2) consecutive modules. | 20% |
|  | The Service Provider does not adhere to timeframes in respect of three (3) consecutive modules. | 40% |
|  | The Service Provider does not adhere to timeframes in respect of any modules. | 60% |
| - Performance Monitoring |  |  |
| - The Service Provider must submit a Monthly Performance Report within six (6) Business Days after the end of a month (Clause 5.2.1.3 of the Services Agreement). | Monthly Performance Report submitted within one (1) Business Day after the six (6) Business Days deadline. | 20% |
|  | Monthly Performance Report submitted within three (3) Business Days after the six (6) Business Days deadline. | 40% |
|  | Monthly Performance Report submitted more than three (3) Business Days after the six (6) Business Days deadline. | 60% |
| - The Monthly Performance Report must include all the items covered in Clauses 5.2.1.5.1 to 5.2.1.5.3 of the Services Agreement. | Monthly Performance Report does not include all items. | 40% |
|  | No Monthly Performance Report is submitted. | 60% |
| - Any failure by the Service Provider to perform any of the obligations set forth in Clause 5.2 of the Services Agreement during any given month. | Any failure by the Service Provider to perform any of the obligations. | 40% |
|  | More than one failure by the Service Provider to perform any of the obligations. | 60% |

| - Special Reports |  |  |
| --- | --- | --- |
| - The Service Provider must submit a close-out report within ten (10) Business Days after the final module of each cohort is held (Clause 9.2 of the Service Agreement). | Close-out report submitted within one (1) working day after the ten (10) Business Days deadline. | 20% |
|  | Close-out report submitted within three (3) working days after the ten (10) Business Days deadline. | 40% |
|  | Close-out report submitted more than three (3) working days after the ten (10) Business Days deadline. | 60% |
| - The Service Provider must submit progress reports per cohort, as and when required (Clause 9.2 of the Service Agreement). | Progress report submitted within one (1) working day after the deadline provided by SARS. | 20% |
|  | Progress report submitted within three (3) working days after the deadline provided by SARS. | 40% |
|  | Progress report submitted more than three (3) working days after the deadline provided by SARS. | 60% |