Musina Customs Vehicle Park: Proposed scope of work for the appointment of paving contractor

Purpose of this document:

To note the details of the scope of work for the installation of paving at the Musina Customs Vehicle Park at the Musina National Defence Force base. Access to the Customs facility is through the back road via the Musina town and not through the main entrance to the Military base from the N1.

The project referred to in this document include any actions required to supply and install paving at the indicated site A Google view-map is attached for ease of reference.

Background

SARS procured a property at the Musina Military base, approximately ten kilometres on the south eastern side of the town Musina. The buildings were constructed on the Department of Public Works land which is shared between the SA National Defence Force, SA Police Service and SA Revenue Service. The buildings were constructed for use by the SA Police Service, SA Police Service and the SA Revenue Service (Customs). The property of concern was handed over to the SA Revenue Service (Customs). An aerial google map view is attached for ease of reference.

The vehicle park is across the road from the Customs warehouse facility.

The following work is completed:

- Firefighting equipment is installed.

- Gates are installed.

- Road on the inside of the Vehicle Park (around the area to be paved) is completed.

The following work has to be completed (by SARS direct contractors) before the paving can be installed:

- Cabling and sleeves in trenches for security and technology installations.

- Masts for security lights.

- Installation of a small guardhouse.

The contractor needs to take note of the following constraints which must be provided for by this project and included in the request for services:

- There is no electricity to the site.

- Water supply is limited. The contractor is to include water required for this project.

- No toilet facilities are available.

- No telecommunications are available.

- The construction of the paving might have to be done in two to three phases to cater for the SARS operational operations. Vehicles are presently being stored on the site and might have to be moved from one part of the site to the other to make provision for the construction. This could result in standing time for the paving contractor and must be included in the Bidder’s submission.

Services required

Refer to the Bill of Quantities and the drawing that form part of this document.

The services of the contractor must include all relevant construction and quality control actions required to deliver the best quality product.

Special / Additional conditions

- Previous work:

  - A list of contactable references (at least three) must be provided where work of a similar size and cost was completed during 2014 and 2015.

  - A project Plan must be provided of one of the previous, similar projects completed during 2014 and 2015.

  - Proof of payment of at least one similar project completed must be supplied.

  - Proof of at least three documents must be supplied to confirm that similar projects were completed.

- Certifying the works completed by means of a Works Completion Certificate.

- The contractor must be willing to conclude a Principle Joint Building Contract Committee Agreement (JBCC) with SARS before the work commence.

- Confirmation that the service provider can commence immediately after the issue of a SARS order and the signing of a JBCC Principle agreement.

- SARS reserve the right to cancel or change the scope of work for this request.

- The cost must include weekly site meetings at Musina of the principle contractor to attend to meetings and to do ‘construction’ monitoring.

- All work must be in compliance of relevant legislative requirements. Relevant certificates must be supplied where applicable.

- The cost must be fixed for the duration of the project. This must be specifically noted in the quotation.

- Use of contingencies must be supported by quotations (using the same rates as used in the main Bill of Quantities) and written approval by SARS.

- Each page of the proposed scope of work document must be initialised. This is to confirm the acceptance of the full scope of work.

- The cost to submit the quotation will be for the account of the potential service provider.

- Omission of any of the items noted in this document might disqualify the service provider.

- A Project Plan must be submitted with the following detail:

  - Activities/Tasks.

  - Duration of activities/tasks.

  - Number of resources used for the activities/tasks.

  - Duration of the whole project.

  - An indication of the work to be done under Provisional Sums.

  - Time allowed for snagging and the fixing of snagging.

  - An indication of afterhours work or work over weekends/holidays.

- A list of at least three suppliers must be provided indicating the supply of paving and related material.

- A Health and Safety Plan must be supplied. The Health and Safety plan and file will have to be updated to be relevant to this project/site after the appointment of the contractor and before work is to commence.

- Details of the guarantees must be provided ie duration and what is guaranteed. The terms and conditions of the guarantee must be included.

- Quotation must be all inclusive meaning to include all cost for:

  - Travelling and accommodation to Musina and back to home base as estimated per the proposed project plan.

  - Any designs to be made.

  - Any investigations to be made.

  - Payment for any information/drawings.

  - Any documentation (sourcing and reporting).

- Service supplier must be willing to conclude a service level agreement with SARS; possibly a CIDB/JBCC Principle agreement. Biiders are to take note that penalties will apply for late delivery where no written extension of time was approved by SARS.

- The contractor must supply proof of:

  - Works Insurance.

  - Public Liability Insurance.

- Payments will only be done after work is completed but can be done on partial completion of works.

- Payment terms are 30 days after approval of an Invoice.

- All Invoices must be in similar for as the Bill of Quantities.

- Progress reports are required on a weekly basis. Photos of progress must be included in the reports.

Google view-map of the Musina Customs Vehicle Park.