## Sheet1
TECHNICAL EVALUATION SCORE SHEET FOR THE REFURBISHMENT OF THE SARS MUSINA CUSTOMS WAREHOUSE STORAGE AREAS.
RFP: ……………………………………………………..
Bidders to include in/attached to the project plan:
Any scope of work as per any provisional sums in the Bill of Quantities ie activities/tasks.
A specific start and end date to clearly indicate the duration of the project. The start and end date will/could be adjusted but the duration remain valid.
Indicate specifically any work scheduled to be done over weekends and indicate it as such on the Project Plan.
Indcate any work scheduled to be done after hours during the week (start and end time ie between 17:00 to 06:00) and indicate it as such on the Project Plan.
Indicate specifically any cleaning or removal of building rubble.
Numbers of resources allocated to tasks.
Clearly indicate weekends/holidays including builders' holidays.
|  | Bidder name/number: |  | Bidder name/number: |  | Bidder name/number: |  | Bidder name/number:
Description | Weight | Points allocated per criteria | Comments by evaluator | Points allocated per criteria | Comments by evaluator | Points allocated per criteria | Comments by evaluator | Points allocated per criteria | Comments by evaluator
Yellow indcate max no of points.
PROVEN CAPABILITY
1.EXPERIENCE (previous work - Section T2 - Form 01) | 15
List of references x 3 (max points) Works completed should be within the past 5 years. | 15
Provide a list of references indicating of works of the following nature including but not limited to: demolishing, building works, fencing, plumbing, ventilation / air conditioning, electrical. One point per applicable item referenced below up to a maximum of five points. References MUST include at least the following items (one point per item): 1) Name of client company. 2) Name of a contact person. 3) Brief description of scope of work. 4) Value of the construction/refurbishment work. 5) Telephone number of contact person. If any of the abovementioned are not indicated and if the reference cannot be confirmed then zero points are allocated for that reference.
2. CURRENT WORKLOAD (Section T2 - Form 02) | 26
Did the contractor indicate the capacity to supply the goods and described in this tender? | 5
Yes = full score.
No = zero score.
Proposed sub-contractors:
Did the contractor indicated whether sub-contractors/in-house contractors will be used or not? (Section T2 - Form 03)
Did indicate sub-contractors/in-house resources will be used = full score | 3
Did not make any indication whether sub-contrcators/inhouse resources will be used will be used = zero score.
Experience of key staff that will be on site (Section T2 - Form 04):
General experience:
Was an indication given on the duration of the person's experience in the general building environment (Section T2 - Form 04):
Yes, more than two years - full score. | 5
No - zero score.
Was an indication given of relevant building industry education (ie building certificate, construction manager certificate, health & safety certificate, etc) (Section T2 - Form 04)?
Yes, = full score. | 5
No - zero score.
Was an inidcation given on the key staff's expert knowledge on demolishing of ablutions and the closing off of plumbing? (Section T2 - Form 04).
Yes = full score | 5
No = zero score
Was the tabel completed indicating the number of personnel that will be on site? (Section T2 Form 05).
Yes, full score (even if a zero number is indicarted). | 3
No = zero score.
3.DETAILED PROGRAMME OF WORKS FOR THIS PROJECT (Section T2 Form 10) | 43
Was a programme /schedule submitted for this project?
Yes | 5
No | 0
Did the programme of works indicate that the work will be done in:
Less than two months? | 15
Two to three months? | 10
Three to four months? | 5
More than four months or no programme submitted? | 0
Was time allowed in the programme for Budgetery and Provisional Sum items allowed for in the BOQ?:
Yes | 8
No
Was time allowed in the programme for the identification and attending to snagging?:
Yes | 5
No | 0
Was time clearly indicated on the project plan for after hours work (during the week and or weekends)?
Yes | 5
No | 0
Quality procedures to be implemented: (Section T2 Form 06)
Was an indication given on the procedure to follow to ensure the services are rendered to the quality and specifications of SARS?
Yes = 2 points | 2
No = zero points
Was the procedure clear and acceptable:
Yes = 3 points | 3
No = zero points.
4. HEALTH & SAFETY PLAN (max points) | 10
Was a Health & Safety plan submitted that could be custom made for this project?
Yes | 10
No | 0
5. GUARANTEES ON WORKMANSHIP | 6
Did the bidder indicate the extend of the guarantees?
Yes | 6
No
TOTAL MAX NO OF POSSIBLE POINTS | 100
Threshold: 70%
Name of the evaluator: …………………………………………………………………………………………………………………………………………………………………….. Date: ………………………………………………………………………………………………