## BDVD1279
WATERPROOFING - DURBAN CUSTOMER HOUSE
SECTION | BILL | PAGE NO | ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
1 | 1 | 25 |  | BILL NO. 1 | H1 | 0
PRELIMINARIES
1 | 1 | 25 |  | BUILDING AGREEMENT AND PRELIMINARIES | H2 | 0
1 | 1 | 25 |  | The JBCC Minor Works Agreement (March 2014 Edition 5.1) prepared by the Joint |  | 0
Building Contracts Committee shall be the applicable building agreement, amended as
hereinafter described
1 | 1 | 25 |  | The JBCC Minor Works Agreement contract data form an integral part of this |  | 0
agreement
1 | 1 | 25 |  | The ASAQS Preliminaries (March 2014 edition) published by the Association of South |  | 0
African Quantity Surveyors for use with the JBCC Minor Works Agreement shall be
deemed to be incorporated in these bills of quantities
1 | 1 | 25 |  | The contractor is deemed to have referred to the abovementioned documents for the |  | 0
full intent and meaning of each clause
1 | 1 | 25 |  | The clauses in the abovementioned documents are hereinafter referred to by clause |  | 0
number and heading only. Where standard clauses or alternatives are not entirely
applicable to this agreement such modifications, corrections or supplements as will
apply are given under each relevant clause heading and such modifications,
corrections or supplements shall take precedence notwithstanding anything to the
contrary contained in the abovementioned documents
1 | 1 | 25 |  | Where any item is not relevant to this agreement such item is marked N/A (signifying |  | 0
"not applicable")
1 | 1 | 25 |  | Additional preliminary clauses are contained in Section "C" hereof |  | 0
1 | 1 | 25 |  | Items left unpriced will be deemed to be covered in prices against other items |  | 0
throughout these bills of quantities and no claim for any extras arising out of the
contractor's omission to price any item will be entertained
1 | 1 | 25 |  | PREAMBLES FOR TRADES | H2 | 0
1 | 1 | 25 |  | The Model Preambles for Trades (2008 edition) as published by the Association of |  | 0
South African Quantity Surveyors shall be deemed to be incorporated in these bills of
quantities and no claims arising from brevity of description of items fully described in
the said Model Preambles will be entertained
1 | 1 | 25 |  | Supplementary preambles are incorporated in these bills of quantities to satisfy the |  | 0
requirements of this project. Such supplementary preambles shall take precedence
over the provisions of the Model Preambles
1 | 1 | 26 |  | The contractor's prices for all items throughout these bills of quantities shall take |  | 0
account of and include for all of the obligations, requirements and specifications given
in the Model Preambles and in any supplementary preambles
1 | 1 | 26 |  | PRICING OF PRELIMINARIES | H2 | 0
1 | 1 | 26 |  | Should the contractor provide a breakdown of charges in terms of clause 20.5.3 of the |  | 0
contract data for the purpose of adjustment of these preliminaries, the amount entered
into the amount column in these preliminaries is to be divided into one or more of the
three categories provided namely fixed (F), value related (V) and time related (T)
1 | 1 | 26 |  | SECTION A: MINOR WORKS AGREEMENT | H2 | 0
1 | 1 | 26 |  | Interpretation (A1 - A7) | H3 | 0
1 | 1 | 26 | 1 | Clause 1.0 - Definitions and interpretation |  |  | 0
1 | 1 | 26 |  | Pricing of bills of quantities | CONT | 0
1 | 1 | 26 |  | The contractor is to allow opposite each item for all costs in connection therewith. All | CONT | 0
prices to include, unless otherwise stated, for all materials, fabrication, conveyance
and delivery, unloading, storing, unpacking, hoisting, labour, setting, fitting and fixing in
position, cutting and waste (except where to be measured in accordance with the
standard system of measurement), patterns, models and templates, plant, temporary
works, returning of packaging, duties, tax, imposts, establishment charges, overheads,
profit and all other obligations arising out of the agreement
1 | 1 | 26 |  | Items left unpriced will be deemed to be covered in prices against other items | CONT | 0
throughout these bills of quantities and no claim for any extras arising out of the
contractor's omission to price any item will be entertained
1 | 1 | 26 |  | Prices for all plant, temporary works, services and other items shall include for the | CONT | 0
supply, maintenance, operating cost and subsequent removal and making good as
necessary
1 | 1 | 26 |  | Value Added Tax | CONT | 0
1 | 1 | 26 |  | Provision is made on the summary page of these bills of quantities for the inclusion of | CONT | 0
Value Added Tax (VAT)
1 | 1 | 26 |  | Clause 1.1 is amended by the addition of the following definitions:
1 | 1 | 26 |  | SPECIAL CONDITIONS: | CONT | 0
The amendments to the JBCC Minor Works Agreement set out in this Bill No 1
(Refer Annexure A)
1 | 1 | 27 |  | RECOVERY STATEMENT: | CONT | 0
The statement prepared and issued in conjunction with each payment certificate by the
principal agent in terms of the JBCC Recovery Statement format
1 | 1 | 27 |  | Clause 1.2 is amended by the addition of the following:
Clause 1.2.6 No waiver or relaxation of any of the provisions or terms of this
agreement (or any agreement or other document issued or executed
pursuant to or in terms of this agreement) shall operate as an
estoppel against a party in respect of any of its rights in terms of this
agreement. No failure by a party to enforce any provision of this
agreement shall constitute a waiver of such provisions or affect in any
way such party's rights to require the performance of such provision at
any time in the future, nor shall a waiver of a subsequent breach
nullify the effectiveness of the provision itself
1 | 1 | 27 |  | Legal status of contractor | CONT | 0
Clause 1.2.7 If the contractor constitutes a joint venture, consortium or other
unincorporated grouping of two or more persons:
1 | 1 | 27 |  | Clause 1.2.7.1 these persons are deemed to be jointly and severally liable to | CONT | 0
the employer for the performance of this agreement;
1 | 1 | 27 |  | Clause 1.2.7.2 these persons shall notify the employer of their leader who has | CONT | 0
authority to bind the contractor and each of these persons; and
1 | 1 | 27 |  | Clause 1.2.7.3 the contractor shall not alter its composition or legal status | CONT | 0
without the prior written consent of the employer
1 | 1 | 27 |  | Clause 1.2.8 The contract documents shall be taken to be mutually\ | CONT | 0
explanatory of one another but in the event of ambiguity, discrepancy,
divergence or inconsistency in or between them, the JBCC Minor
Works Agreement as amended by the special conditions shall prevail
over all other contract documents. As between the JBCC Minor Works
Agreement and the special conditions, the special conditions shall
prevail
1 | 1 | 27 |  | F:............................. V:............................ T:............................ | Item | 1
1 | 1 | 27 | 2 | Clause 2.0 - Law, regulations and notices | CONT | 0
Clause 2.0 is amended by the addition of the following:
1 | 1 | 27 |  | Clause 2.6 - Health and safety | CONT | 0
1 | 1 | 28 |  | Without limiting the generality of the provisions of clause 2.0, the contractor's attention | CONT | 0
is drawn to the provisions of Construction Regulations issued in terms of the
Occupational Health and Safety Act, 1993. It is specifically stated that the employer
shall prepare a documented health and safety specification for the works and that the
employer shall ensure that the contractor has made provision for the cost of health and
safety measures during the execution of the works. The contractor shall price
opposite this item for compliance with the act and the regulations and the reasonable
provisions of the aforementioned health and safety specification [2.1]
1 | 1 | 28 |  | The contractor shall take all reasonable precautions to maintain the health and safety | CONT | 0
of persons in and about the execution of the works. Without limitation the contractor
hereby:
1 | 1 | 28 |  | Clause 2.6.1 accepts that the employer will appoint him as the Principal | CONT | 0
Contractor (as defined and provided for under the Construction
Regulations 2014 (as amended), promulgated under the Occupational
Health & Safety Act 85 of 1993 (as amended) (the Construction
Regulations)) for the site;
1 | 1 | 28 |  | Clause 2.6.2 acknowledges and confirms that the contract sum includes a | CONT | 0
sufficient amount for proper compliance with the employer's Health
and Safety Specification, the Construction Regulations, all applicable
health & safety laws and regulations and the health and safety rules,
guidelines and procedures provided for in this agreement and
generally for the proper maintenance of health and safety in and about
the execution of works; and
1 | 1 | 28 |  | Clause 2.6.3 undertakes, in and about the execution of the works, to conform | CONT | 0
to and comply with the Construction Regulations and with all
applicable health and safety laws and regulations and rules and
guidelines and
procedures otherwise provided for under the agreement and shall
ensure that all subcontractors, employees and others under the
contractor's direction and control, likewise observe and comply with
the foregoing
1 | 1 | 28 |  | Clause 2.6.4 Prepare and agree with the health and safety consultant the | CONT | 0
health and safety plan for the works
Clause 2.6.5 Co-operate with the health and safety consultant in all respects
1 | 1 | 28 |  | F:............................. V:............................ T:............................ | Item | 1
1 | 1 | 28 | 3 | Clause 3.0 - Offer, acceptance and assignment | Item | 1
F:............................. V:............................ T:............................
1 | 1 | 28 | 4 | Clause 4.0 - Contract documents | CONT | 0
1 | 1 | 29 |  | F:............................. V:............................ T:............................ | Item | 1
1 | 1 | 29 | 5 | Clause 5.0 - Employer's agents | CONT | 0
1 | 1 | 29 | 6 | Clause 6.0 - Principal agent | Item | 1
F:............................. V:............................ T:............................
1 | 1 | 29 | 7 | Clause 7.0 - Design responsibility | Item | 1
F:............................. V:............................ T:............................
1 | 1 | 29 |  | Insurance and security (A8-A9) | H3 | 0
1 | 1 | 29 | 8 | Clause 8.0 - Works risk, Risks, Indemnities and Insurances | Item | 1
F:............................. V:............................ T:............................
1 | 1 | 29 | 9 | Clause 9.0 - Security | CONT | 0
1 | 1 | 29 |  | Clause 9.0 is amended by the addition of the following: | CONT | 0
1 | 1 | 29 |  | Clause 9.9 The contractor shall ensure that the guarantee for construction is | CONT | 0
valid and enforceable until the certificate of final completion is issued
to the contractor and all payments reflected as due to the employer in
the final payment certificate have been paid in full (hereinafter
collectively "the expiry events"). If the terms of the guarantee for
construction specify its expiry date and the expiry events have not
occurred twenty (20) working days prior to the said expiry date, the
contractor shall promptly extend the validity of the guarantee for
construction until the expiry events have occurred. If the contractor
fails to so extend the validity of the guarantee for construction, the
employer shall be entitled to payment from the contractor of the then
guaranteed sum, which shall then be retained by the employer as
cash security. The principal agent shall accordingly, and immediately,
issue a payment certificate certifying the guaranteed sum as a
payment due to the employer. If the contractor fails to make payment
of the amount certified upon presentation of the payment certificate,
the employer may claim the amount under the guarantee for
construction
1 | 1 | 29 |  | The amount so claimed against and paid under the guarantee for |  |  |  | 0
construction shall be reimbursed to the contractor if and when the
guarantee for construction is reinstated, extended or substituted in
compliance with the above (as the case may be) and the principal
agent shall forthwith issue a payment certificate certifying the amount
so due to the contractor
1 | 1 | 29 |  | F:............................. V:............................ T:............................ | Item | 1
1 | 1 | 30 |  | Execution (A10 - A14) | H3 | 0
1 | 1 | 30 | 10 | Clause 10.0 - Employer | CONT | 0
1 | 1 | 30 | 11 | Clause 11.0 - Contractor | Item | 1
1 | 1 | 30 |  | Clause 11.2.5 - Notice boards | CONT | 0
Notice board
1 | 1 | 30 |  | The contractor shall erect in a position approved by the principal agent, maintain and | Item | 1
remove at completion a notice board as recommended by the South African Institute
of Architects listing the names and logos of the employer, the contractor and the
professional consultants. No subcontractor or supplier notice boards may be erected
[11.2.5]
F:............................. V:............................ T:............................
1 | 1 | 30 | 12 | Clause 12.0 - Setting out | Item | 1
Clause 12.0 is amended by the addition of the following:
Clause 12.4 - Encroachments
Clause 12.4.1The contractor shall notify the principal agent if any
encroachment of adjoining foundations, buildings, structures,
pavements, boundaries, services, etc exist in order that the necessary
arrangements may be made for the rectification of any such
encroachments [12.2.1]
F:............................. V:............................ T:............................
1 | 1 | 30 | 13 | Clause 13.0 - Direct contractors | CONT | 0
Clause 13.0 is amended by the addition of the following:
Clause 13.4 Attendance on direct contractors
In respect of direct contractors the contractor shall:
1 | 1 | 30 |  | Clause 13.4.1 Designate an area for the direct contractor to establish a | CONT | 0
temporary office and workshop and storage of equipment and
materials
1 | 1 | 30 |  | Clause 13.4.2 Allow the use of personnel welfare facilities, where provided | CONT | 0
1 | 1 | 30 |  | Clause 13.4.3 Provide water, lighting and single phase electric power to a | CONT | 0
position within 50m of the place where the direct contract work is to be
carried out, other than fuel or power for commissioning of any
installation
1 | 1 | 31 |  | Clause 13.4.4 Permit the direct contractor to use erected scaffolding, hoisting | CONT | 0
facilities, etc provided by the contractor, in common with others having
the like right while it remains erected on the site [16.1]
1 | 1 | 31 |  | F:............................. V:............................ T:............................ | Item | 1
1 | 1 | 31 | 14 | Clause 14.0 - Contract instructions | Item | 1
Site instructions
Instructions issued on site are to be recorded in a site instruction book which is to be
supplied and maintained on site by the contractor
F:............................. V:............................ T:............................
1 | 1 | 31 |  | Completion (A15 - A18) | H3 | 0
1 | 1 | 31 | 15 | Clause 15.0 - Practical completion | Item | 1
Clause 15.0 is amended by the addition of:
Clause 15.6 If the contractor does not achieve practical completion by the
applicable date for practical completion [15.0], then the employer
shall, with the prior written agreement of the contractor (which shall
not be unreasonably delayed or withheld), be entitled to take
possession of the works and the site and occupy and operate the
building as if practical completion has been achieved (but practical
completion shall not be deemed to have taken place and the
applicable certificate of practical completion shall not be issued)
F:............................. V:............................ T:............................
1 | 1 | 31 | 16 | Clause 16.0 - Defects liability period and final completion | Item | 1
F:............................. V:............................ T:............................
1 | 1 | 31 | 17 | Clause 17.0 - Revision of date for practical completion | CONT | 0
Clause 17.0 is amended by the addition of the following:
Clause 17.6 Substitution of materials and goods
Clause 17.6.1 The removal or substitution of any materials and goods which do not
conform to the specification or the contract drawings shall not
constitute grounds for the extension of the construction period nor
for the adjustment of the contract value [14.1.8, 17.1 & 2]
1 | 1 | 32 |  | Clause 17.7 No revision to the date for practical completion shall be | Item | 1
considered unless the contractor demonstrates, to the reasonable
satisfaction of the principal agent and on the basis of the current
programme or other programme acceptable to the principal agent for
this purpose, that the delay is on the critical path to practical
completion of the works or section thereof (as the case may be)
F:............................. V:............................ T:............................
1 | 1 | 32 | 18 | Clause 18.0 - Penalty for late or non-completion | Item | 1
F:............................. V:............................ T:............................
1 | 1 | 32 |  | Payment (A19 - A20) | H3 | 0
1 | 1 | 32 | 19 | Clause 19.0 - Payment | CONT | 0
Clause 19.0 is amended by the addition of the following:
1 | 1 | 32 |  | Clause 19.14 - Materials and goods stored off site | CONT | 0
Clause 19.14.1The inclusion of materials and goods stored off site in the
amount
authorised for payment shall be at the sole discretion of the principal
agent and such inclusion shall only be considered upon the provision,
by the contractor, of an approved security [19.3.2]
1 | 1 | 32 |  | Clause 19.15 - Fluctuations in costs | CONT | 0
Clause 19.15.1 All fluctuations in costs, with the exception of fluctuations in the rate of
Value Added Tax, shall be for the account of the contractor
1 | 1 | 32 |  | Clause 19.16 - Prices submitted | Item | 1
Clause 19.16.1 Where prices are submitted by the contractor during the
progress of the works in respect of contract instructions or in regard to
a claim under the terms of the agreement and notwithstanding the fact
that such prices may be used in an interim payment certificate, there
is to be no presumption of acceptance. Should the principal agent
wish to accept any such prices prior to the issue of the certificate of
final completion, it shall be in writing
F:............................. V:............................ T:............................
1 | 1 | 32 | 20 | Clause 20.0 - Adjustment of the contract value and final account | CONT | 0
1 | 1 | 33 |  | Clause 20.10 - Cost of claims | Item | 1
Clause 20.10.1 All costs incurred by the contractor in the preparation of claims
shall be borne by the contractor
F:............................. V:............................ T:............................
1 | 1 | 33 |  | Termination (A21) | H3 | 0
1 | 1 | 33 | 21 | Clause 21.0 - Termination | CONT | 0
1 | 1 | 33 |  | Dispute resolution (A22) | H3 | 0
1 | 1 | 33 | 22 | Clause 22.0 - Dispute resolution | Item | 1
F:............................. V:............................ T:............................
1 | 1 | 33 | 23 | Agreement | Item | 1
The required information of the parties and the amount of the contract sum shall be
inserted in the agreement for signature of the agreement by the parties
F:............................. V:............................ T:............................
1 | 1 | 33 | 24 | Contract data | CONT | 0
Before submission of his tender the contractor is to complete the tenderer's selection
in the contract data
1 | 1 | 33 |  |  | H2 | 0
SECTION B: PRELIMINARIES
1 | 1 | 33 |  | Interpretation (B1) | H3 | 0
1 | 1 | 33 | 25 | Clause 1.1 - Definitions | Item | 1
F:............................. V:............................ T:............................
1 | 1 | 33 | 26 | Clause 1.2 - Interpretation | Item | 1
F:............................. V:............................ T:............................
1 | 1 | 33 |  | Documents (B2) | H3 | 0
1 | 1 | 33 | 27 | Clause 2.1 - Checking of documents | Item | 1
F:............................. V:............................ T:............................
1 | 1 | 34 | 28 | Clause 2.2 - Provisional bills of quantities | Item | 1
F:............................. V:............................ T:............................
1 | 1 | 34 | 29 | Clause 2.3 - Availability of construction information | Item | 1
F:............................. V:............................ T:............................
1 | 1 | 34 |  | Previous work and adjoining properties (B3) | H3 | 0
1 | 1 | 34 | 30 | Clause 3.1 - Previous work - dimensional accuracy | Item | 1
F:............................. V:............................ T:............................
1 | 1 | 34 | 31 | Clause 3.2 - Previous work - defects | Item | 1
F:............................. V:............................ T:............................
1 | 1 | 34 | 32 | Clause 3.3 - Inspection of adjoining properties | Item | 1
F:............................. V:............................ T:............................
1 | 1 | 34 |  | Samples, shop drawings and manufacturer's instructions (B4) | H3 | 0
1 | 1 | 34 | 33 | Clause 4.1 - Samples of materials | Item | 1
F:............................. V:............................ T:...........................
1 | 1 | 34 | 34 | Clause 4.2 - Workmanship samples | Item | 1
F:............................. V:............................ T:............................
1 | 1 | 34 | 35 | Clause 4.3 - Shop drawings | Item | 1
F:............................. V:............................ T:............................
1 | 1 | 34 | 36 | Clause 4.4 - Compliance with manufacturer's instructions | Item | 1
F:............................. V:............................ T:............................
1 | 1 | 34 |  | Deposits and fees (B5) | H3 | 0
1 | 1 | 34 | 37 | Clause 5.1 - Deposits and fees | Item | 1
F:............................. V:............................ T:............................
1 | 1 | 35 |  | Temporary services (B6) | H3 | 0
1 | 1 | 35 | 38 | Clause 6.1 - Water | Item | 1
F:............................. V:............................ T:............................
1 | 1 | 35 | 39 | Clause 6.2 - Electricity | Item | 1
F:............................. V:............................ T:............................
1 | 1 | 35 | 40 | Clause 6.3 - Ablution and welfare facilities | Item | 1
F:............................. V:............................ T:............................
1 | 1 | 35 | 41 | Clause 6.4 - Communication facilities | Item | 1
F:............................. V:............................ T:............................
1 | 1 | 35 |  | Prime cost amounts (B7) | H3 | 0
1 | 1 | 35 | 42 | Clause 7.1 - Responsibility for prime cost amounts | Item | 1
F:............................. V:............................ T:............................
1 | 1 | 35 |  | Attendance on subcontractors (B8) | H3 | 0
1 | 1 | 35 | 43 | Clause 8.1 - General attendance | N/A | 0
F:............................. V:............................ T:............................
1 | 1 | 35 | 44 | Clause 8.2 - Special attendance | N/A | 0
F:............................. V:............................ T:............................
1 | 1 | 35 |  | General (B9) | H3 | 0
1 | 1 | 35 | 45 | Clause 9.1 - Protection of the works | Item | 1
F:............................. V:............................ T:............................
1 | 1 | 35 | 46 | Clause 9.2 - Protection/isolation of existing/sectionally occupied works | CONT | 0
1 | 1 | 35 |  | Occupied buildings during construction | Item | 1
The building will be occupied during construction and contractor need to ensure that all
materials and labour needs to be delivered to roof level without interfering with the
daily operations of the builsing
F:............................. V:............................ T:............................
1 | 1 | 36 | 47 | Clause 9.3 - Security of the works | Item | 1
F:............................. V:............................ T:............................
1 | 1 | 36 | 48 | Clause 9.4 - Notice before covering work | Item | 1
F:............................. V:............................ T:............................
1 | 1 | 36 | 49 | Clause 9.5 - Disturbance | Item | 1
F:............................. V:............................ T:............................
1 | 1 | 36 | 50 | Clause 9.6 - Environmental disturbance | Item | 1
Clause 9.6 is amended by the addition of the following:
The contractor shall be responsible for and take all precautions in
controlling by whatever means necessary all forms of pollution during
the construction period due inter alia to noise, artificial light,
wind-blown sand, dust, deposits of mud, etc
F:............................. V:............................ T:............................
1 | 1 | 36 | 51 | Clause 9.7 - Works cleaning and clearing | Item | 1
F:............................. V:............................ T:............................
1 | 1 | 36 | 52 | Clause 9.8 - Vermin | Item | 1
F:............................. V:............................ T:............................
1 | 1 | 36 | 53 | Clause 9.9 - Overhand work | Item | 1
F:............................. V:............................ T:............................
1 | 1 | 36 |  | Schedule (B10) | H3 | 0
1 | 1 | 36 |  | Information for completion of schedule | CONT | 0
Information necessary for elections and completion of those clauses contained in the
schedule which are necessary for tender purposes is given hereunder. Where no
information is given it shall mean that no specific requirements are expected or that
the clause is not relevant to this specific contract
Refer to preliminaries schedule Annexure 2
1 | 1 | 37 |  | SECTION C: SPECIFIC PRELIMINARIES | H2 | 0
1 | 1 | 37 | 54 | Warranties for materials and workmanship | CONT | 0
Where warranties for materials and/or workmanship are called for, the contractor shall
obtain a written warranty, addressed to the employer, from the entity supplying the
materials and/or doing the work and shall deliver same to the principal agent on the
final completion of the contract
1 | 1 | 37 |  | The warranty shall state that workmanship, materials and installation are warranted for | CONT | 0
a specific period from the date of final completion and that any defects that may arise
during the specified period shall be made good at the expense of the entity supplying
the materials and/or doing the work, upon written notice to do so
1 | 1 | 37 |  | The warranty will not be enforced if the work is damaged by defects in the execution of | Item | 1
the works, in which case the responsibility for replacement shall rest entirely with the
contractor
F:............................. V:............................ T:............................
1 | 1 | 37 | 55 | Overtime | Item | 1
Should overtime be required to be worked for any reason whatsoever, the costs of
such overtime is to be borne by the contractor unless the principal agent has
specifically authorised, in writing, prior to execution thereof, that costs for such
overtime are to be borne by the employer
F:............................. V:............................ T:............................
1 | 1 | 37 | 56 | Co-operation of the contractor for cost management | Item | 1
It is specifically agreed that the contractor accepts the obligation of assisting the
principal agent in implementing proper cost management. The contractor will be
advised by the principal agent of all cost management procedures which will be
implemented to ensure that the final building cost does not exceed the budget
F:............................. V:............................ T:............................
1 | 1 | 37 | 57 | Overloading | Item | 1
The contractor shall take all necessary steps to ensure that no damage occurs due to
overloading of any portion of the works or temporary works eg scaffolding, etc. The
contractor shall submit details of his proposed loading, storage, plant erection, etc to
the principal agent for approval prior to proceeding with such loading, storing or
erecting and shall comply with and pay for the principal agent's requirements in
connection with the provision of temporary support work, etc. Any damage caused to
the works by overloading shall be made good by the contractor at his sole expense
F:............................. V:............................ T:............................
1 | 1 | 38 | 58 | Testing of flat roof waterproofing for watertightness | Item | 1
Flat roof waterproof areas shall be prepared with small sand dykes around them of a
size and enclosing an area approved by the principal agent, flooded with water and
kept "ponded" for at least forty (40) hours as a test to ensure the watertightness of the
waterproofing and before any further construction work is carried out above the
waterproofing
F:............................. V:............................ T:............................
1 | 1 | 38 | 59 | Broad based black economic empowerment (BBBEE) | CONT | 0
Tenders submitted will be evaluated taking into account their empowerment rating
The employer will be monitoring the black economic empowerment status of the
contractor throughout the execution of the works
1 | 1 | 38 |  | The contractor is to submit to the principal agent on an annual basis a schedule of | Item | 1
spend, split into vendors engaged and suppliers indicating their BBBEE rating
including proof of the said rating
F:............................. V:............................ T:............................
1 | 1 | 38 | 60 | Advertising rights | Item | 1
The employer may elect to contract with advertising agencies for the erection of
advertising hoardings, banners, wraps or the like for the duration of the contract. The
contractor shall not prevent such an arrangement and will assist in the facilitation of
same. Position and type of advertising structure to be agreed with the principal agent
so as not to hinder the contractor in the meeting of his obligations under this
agreement
F:............................. V:............................ T:............................
1 | 1 | 38 | 61 | Confidentiality | Item | 1
The contractor undertakes to maintain in confidence any and all information regarding
this project and shall obtain appropriate similar undertakings from all suppliers. Such
information shall not be used in any way except in connection with the execution of the
works
No information regarding this project shall be published or disclosed without the prior
written consent of the employer
F:............................. V:............................ T:............................
1 | 1 | 39 | 62 | Media releases | Item | 1
All rights of publication of articles in the media, together with any advertising relating
thereto or in any way connected with this project, shall vest with the employer
The contractor shall not, without the prior written consent of the employer, cause any
statement or advertisement to be printed, screened or aired by the media
F:............................. V:............................ T:............................
1 | 1 | 39 |  | SUMMARY OF CATEGORIES | H3 | 0
1 | 1 | 39 |  | Category : Fixed R........................................ |  | 0
Category : Value R........................................
Category : Time R........................................
2 | 1 | 41 |  | SECTION NO. 2 | H1 | 0
2 | 1 | 41 |  | BUILDING WORK | H1 | 0
2 | 1 | 41 |  | BILL NO 1 | H1 | 0
2 | 1 | 41 |  | ALTERATIONS | H1 | 0
2 | 1 | 41 |  | For preambles see "Model Preambles for Trades" |  | 0
2 | 1 | 41 |  | EXISTING FURNITURE, EQUIPMENT, ETC | H2 | 0
2 | 1 | 41 |  | The Contractor shall not remove or damage any furniture, |  | 0
equipment or similar items that belong to the Department
except when specifically described in the items to follow:
2 | 1 | 41 |  | The Contractor must give the Representative/Agent sufficient |  | 0
notice if the removal of these items are required before any
prescribed alterations can be done
2 | 1 | 41 |  | Work and material | H3 | 0
2 | 1 | 41 |  | The work to be done and materials to be used in the alterations |  | 0
are to be similar to those specified in the new work in so far as
they apply
2 | 1 | 41 |  | PRICES | H2 | 0
2 | 1 | 41 |  | Prices are to include for carting away from site all materials not |  | 0
specifically mentioned as being stored on site for re-use or
handed over to the Director and all rubbish, debris, etc arising
from the alterations, etc and for making good all work damaged
or disturbed to the approval of the Director
2 | 1 | 41 |  | Dimensions | H3 | 0
2 | 1 | 41 |  | All dimensions and sizes referred to in this bill are approximate |  | 0
2 | 1 | 41 |  | ---oOo--- |  | 0
2 | 1 | 41 |  | REMOVAL OF EXISTING WORK | H2 | 0
2 | 1 | 41 |  | Break up and remove mass concrete | H3 | 0
2 | 1 | 41 | 1 | Condensor plinths | m3 | 10
2 | 1 | 42 |  | Break down and remove masonry | H3 | 0
2 | 1 | 42 | 2 | 230mm Brick walls | m2 | 98
2 | 1 | 42 |  | Take out/off and remove sundry metalwork | H3 | 0
2 | 1 | 42 | 3 | Steel balustrades 0.90m high from concrete stairs, including | m | 119
making good granolithic finish
2 | 1 | 42 |  | Take out and remove cast iron drainage outlets, including | H3 | 0
preparing for connection of new outlets to existing piping and
making good waterproofing screeds
2 | 1 | 42 | 4 | 110mm Diameter 180 degree fullbore outlet | m | 16
2 | 1 | 42 |  | Hack up/off and remove granolithic, screeds or plaster from | H3 | 0
concrete or masonry and prepare surfaces for new screeds or
plaster
2 | 1 | 42 | 5 | Cement screed in patches average 50mm thick | m2 | 57
2 | 1 | 42 |  | Taking up and removing waterproofing membrane coverings, | H3 | 0
etc
2 | 1 | 42 | 6 | Waterproof membrane covering including preparing existing | m2 | 342
precast coping set to falls for new waterproofing membrane
covering.
2 | 1 | 42 | 7 | Waterproof membrane covering including preparing existing | m2 | 551
plastered walls for new waterproofing membrance covering.
2 | 1 | 42 |  | PREPARATORY WORK TO EXISTING SURFACES | H2 | 0
2 | 1 | 42 |  | Preparatory work to existing surfaces | H3 | 0
2 | 1 | 42 | 8 | Scabble existing concrete floors to receive screed | m2 | 57
2 | 1 | 42 |  | MAKE GOOD FINISHES, ETC | H2 | 0
2 | 1 | 42 |  | Make good screeds | H3 | 0
2 | 1 | 42 | 9 | Average 50mm thick to floors in patches | m2 | 57
2 | 2 | 44 |  | SECTION NO. 2 | H1 | 0
2 | 2 | 44 |  | BUILDING WORK | H1 | 0
2 | 2 | 44 |  | BILL NO. 2 | H1 | 0
2 | 2 | 44 |  | CONCRETE, FORMWORK & REINFORCEMENT | H1 | 0
2 | 2 | 44 |  | For preambles see "Model Preambles for Trades" |  | 0
2 | 2 | 44 |  | SUPPLEMENTARY PREAMBLES | H2 | 0
2 | 2 | 44 |  | ---oOo--- |  | 0
2 | 2 | 44 |  | CONCRETE | H2 | 0
2 | 2 | 44 |  | REINFORCED CONCRETE | H2 | 0
2 | 2 | 44 |  | Concrete Class 25/19 | H3 | 0
2 | 2 | 44 | 1 | Airconditioing plinths 1200 x 600 x 100mm thick | No | 15
2 | 2 | 44 |  | GENERAL FORMWORK | H2 | 0
2 | 2 | 44 |  | Class F1 formwork to sides | H3 | 0
2 | 2 | 44 | 2 | Edges, risers, ends, reveals, etc. not exceeding 300mm | m | 54
high/wide
2 | 2 | 44 |  | REINFORCEMENT | H2 | 0
2 | 2 | 44 |  | Prices for mesh reinforcement are to include for all cutting and |  | 0
waste, bending and notchings.
2 | 2 | 44 |  | Mesh reinforcement | H3 | 0
2 | 2 | 44 | 3 | Mesh reinforcement with mesh reference number 193 laid in | m2 | 11
concrete slabs, floor slabs, ramps, hollow block slab
construction, etc. with 300mm side and end laps (measured
net)
2 | 3 | 45 |  | SECTION NO. 2 | H1 | 0
2 | 3 | 45 |  | BUILDING WORK | H1 | 0
2 | 3 | 45 |  | BILL NO. 3 | H1 | 0
2 | 3 | 45 |  | WATERPROOFING | H1 | 0
2 | 3 | 45 |  | For preambles see "Model Preambles for Trades" |  | 0
2 | 3 | 45 |  | SUPPLEMENTARY PREAMBLES | H2 | 0
2 | 3 | 45 |  | PRICES | H2 | 0
2 | 3 | 45 |  | In addition, prices for all waterproofing are to include for all |  | 0
cutting, sealing and protection against injury. All work to be left
completely watertight at completion
2 | 3 | 45 |  | Waterproofing | H4 | 0
2 | 3 | 45 |  | Waterproofing of roofs, basements, etc shall be laid under a ten |  | 0
year guarantee. Waterproofing to roofs shall be laid to even
falls to outlets, etc with necessary ridges, hips and valleys.
Descriptions of sheet or membrane waterproofing shall be
deemed to include additional labour to turn-ups and turn-downs
2 | 3 | 45 |  | ---oOo--- |  | 0
2 | 3 | 45 |  | WATERPROOFING TO FLAT ROOFS | H2 | 0
2 | 3 | 45 |  | One layer Derbigum SP4 waterproofing membrane sealed by | H4 | 0
means of 'torchfusion' or Coldbond 90 adhesive with 75mm
side laps and 100mm end laps, laid under a ten-year
guarantee, to receive paint or stone protection (elsewhere)
2 | 3 | 45 | 1 | Flat roofs | m2 | 3724
2 | 3 | 45 | 2 | On tops and sides of inverted beams. | m2 | 551
2 | 3 | 45 | 3 | Additional membrane not exceeding 300mm girth at turn-ups | m | 737
and turn-downs
2 | 3 | 45 | 4 | Walls as cover flashing strips not exceeding 300mm girth, | m | 683
including sealing top edges with mastic in and including
grooves in masonry or concrete
2 | 3 | 45 | 5 | Additional membranes, gussets, collars, etc around pipes and | No | 34
into outlets, etc
2 | 3 | 46 |  | PROTECTIVE ROOFING PAINT | H2 | 0
2 | 3 | 46 |  | Derbigum | H3 | 0
2 | 3 | 46 |  | Two coats bituminous aluminium paint: | H4 | 0
2 | 3 | 46 | 6 | On waterproofing to roofs. | m2 | 4275
2 | 4 | 48 |  | SECTION NO. 2 | H1 | 0
2 | 4 | 48 |  | BUILDING WORK | H1 | 0
2 | 4 | 48 |  | BILL NO. 4 | H1 | 0
2 | 4 | 48 |  | PLUMBING | H1 | 0
2 | 4 | 48 |  | For preambles see "Model Preambles for Trades" |  | 0
2 | 4 | 48 |  | SUPPLEMENTARY PREAMBLES | H2 | 0
2 | 4 | 48 |  | General | H4 | 0
2 | 4 | 48 |  | Descriptions of cast iron roof outlets shall be deemed to include |  | 0
joints to existing pipes and fitting into existing concrete slab
2 | 4 | 48 |  | ---oOo--- |  | 0
2 | 4 | 48 |  | RAINWATER DISPOSAL | H2 | 0
2 | 4 | 48 |  | Saint-Gobain Full-Flow ductile iron outlets | H4 | 0
2 | 4 | 48 | 1 | 100mm 180 Degree vertical dome roof outlet | No | 16
2 | 5 | 49 | 1 | Alterations | Page | -43-
2 | 5 | 49 | 2 | Concrete, Formwork & Reinforcement | Page | -44-
2 | 5 | 49 | 3 | Waterproofing | Page | -47-
2 | 5 | 49 | 4 | Plumbing and Drainage | Page | -48-
3 | 1 | 50 | 1 | Preliminaries | Page | -40-
3 | 1 | 50 | 2 | Building Works | Page | -49-
BUDGETARY ALLOWANCES
Sundry specialist work
|  |  |  | Provide an amount of R30 000.00 (thirty thousand rand) for | Item | 1
sundry specialist work Item 30 000 00
|  |  |  | Allow for overheads and profit Item | Item | 1
3 | 1 | 50 |  | NET TOTAL: EXCLUDING VALUE-ADDED TAX | ST | 0 |  | Sub Total
3 | 1 | 50 |  | ADD: 15% ON THE ABOVE TOTAL FOR CONTINGENCIES | VAT | 15 |  | 2015-11-16 15:34
3 | 1 | 50 |  | SUBTOTAL | ST | 0 |  | Sub Total
3 | 1 | 50 |  | ADD: 14% (FOURTEEN PERCENT) on the above total for | VAT | 14 |  | 2015-11-16 15:35
VALUE ADDED TAX
TOTAL ITEMS | 243 | MSD ITEMS | 76 | RATE# | 0
END | ASCII